## Slide 1: GBUS 8621: Project Management Project Planning: Project Scope, Network Analysis and Critical Path Echelon, Inc.'s Software Product Release
Yael Grushka-Cockayne

## Slide 2: Project Planning and Management
Definition
Goal
Organization
Planning
Detailed Scope
(Work Breakdown Structure)
Execution
Scope
Time
Budget
Dependencies
Schedule
Resources
Trade-Offs
Risk Analysis
Status Reporting
Corrections
Close Project
Postmortem

## Slide 3: Project Definition
Project Goal: OptFactory Mini-Release
Project Organization: Mike, Engineering, Professional Services, Sales, Marketing departments.
Scope: Build the software, train the customer-facing groups and promote the release
Time: ASAP
Budget: Compromise

## Slide 4: Project Planning: Scope
Work Breakdown Structure (WBS)

## Slide 5: Project Planning: Durations
Task Description Duration Completed in Max. Possible Resource Required
(Days) advance Reduction (Days)
A Finalize Mini-release Feature Specifications 2 - - Product Manager B Feature 1 Engine Development 8 A - Product Architect
C Feature 1 Component Development 13 B 4 Component Developer D Feature 1 Web/Interface Development 10 C 3 Web Developer
Feature 2 Engine Development 15 A - Product Architect
Feature 2 Component Development 7 E 2 Component Developer G Feature 2 Web/Interface Development 4 F 2 Web Developer
H Integrate Code 4 D,G - Product Architect I Test and Fix 21 H 5 Q&A Engineer J Prepare Marketing Message 5 A - Product Manager
K Train PSO and Pre-Sales 2 H,J - Product Manager L Educate Sales Force 2 J - Product Manager M Prepare Marketing Material 10 J 4 Marketing Specialist N Announce Release 1 I,K,L,M - Marketing VP

## Slide 6: Project Planning: Dependencies
Dependency Matrix

## Slide 7: Project Planning: Schedule
Network Diagram
Task A
(2 Days)
Task B
(8 Days)
Task C
(13 Days)
Task F
(7 Days)
Task E
(15 Days)
Task D
(10 Days)
Task G
(4 Days)
Task J
(5 Days)
Task H
(4 Days)
Task K
(2 Days)
Task L
(2 Days)
Task M
(10 Days)
Task I
(21 Days)
Task N
(1 Days)

## Slide 8: Project Planning: Critical Path Method
Task A
(2)
Task B
(8)
Task C
(13)
Task F
(7)
Task E
(15)
Task D
(10)
Task G
(4)
Task J
(5)
Task H
(4)
Task K
(2)
Task L
(2)
Task M
(10)
Task I
(21)
Task N
(1)
Phase 1: proceed left to right identifying the earliest start (ES) and earliest finish (EF) for each task
Task name
(duration)
ES EF
LS LF
Phase 2: proceed right to left identifying the latest start (LS) and latest finish (LF) for each task

## Slide 9: Project Planning: Critical Path Method
Task A
(2)
Task B
(8)
Task C
(13)
Task F
(7)
Task E
(15)
Task D
(10)
Task G
(4)
Task J
(5)
Task H
(4)
Task K
(2)
Task L
(2)
Task M
(10)
Task I
(21)
Task N
(1)
Task name
(duration)
ES EF
LS LF
0
0
2
2
37
56
39
58
10
10
23
23
23
23
33
33
33
33
37
37
37
37
58
58
58
58
59
59
2
43
7
48
7
56
9
58
7
48
17
58
2
2
10
10
2
7
17
22
17
22
24
29
24
29
28
33

## Slide 10: Project Planning: Critical Path Method
Task A
(2)
Task B
(8)
Task C
(13)
Task F
(7)
Task E
(15)
Task D
(10)
Task G
(4)
Task J
(5)
Task H
(4)
Task K
(2)
Task L
(2)
Task M
(10)
Task I
(21)
Task N
(1)
Task name
(duration)
ES EF
LS LF
0
0
2
2
37
56
39
58
10
10
23
23
23
23
33
33
33
33
37
37
37
37
58
58
58
58
59
59
2
43
7
48
7
56
9
58
7
48
17
58
2
2
10
10
2
7
17
22
17
22
24
29
24
29
28
33

## Slide 11: Project Planning: With Resources Constraints
Task A
(2)
Task B
(8)
Task C
(13)
Task F
(7)
Task E
(15)
Task D
(10)
Task G
(4)
Task J
(5)
Task H
(4)
Task K
(2)
Task L
(2)
Task M
(10)
Task I
(21)
Task N
(1)
Task name
(duration)
ES EF
LS LF
0
0
2
2
40
59
42
61
10
13
23
26
23
26
33
36
36
36
40
40
40
40
61
61
61
61
62
62
2
43
7
48
7
57
9
59
7
51
17
61
2
2
10
10
10
10
25
25
25
25
32
32
32
32
28
33